## Project
PROJECT PLANNER
Project Details | Durations |  |  | Predecessors | Assigned To | % Complete | Status | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30
| Days | Start | End
Project Duration | 192 | 2023-10-22 | 2024-04-30 |  |  | 30.21%
PROJECT Project Commencement | 7 | 2023-10-29 | 2023-11-05 |  |  | 114.3%
Contract Award (LOA) | 10 | 2023-11-06 | 2023-11-16 |  |  | 110%
Mobilization | 1 | 2023-11-17 | 2023-11-17 |  |  | 100%
PROJECT Material approvals | 15 | 2023-11-18 | 2023-12-03 |  |  | 106.7%
Material Submittal for ( Sand, Seeds, Fertiliser, Fungicides, Pesticides and Peatmoss ) | 22 | 2023-12-04 | 2023-12-26 |  |  | 68.18%
Materials approvals | 1 | 2023-12-27 | 2023-12-27 |  |  | -800%
Procurement | 3 | 2023-12-28 | 2023-12-31 |  |  | -300%
Road freight SSMG From UAE To KSA for (1000 Kg ) | 8 | 2024-01-01 | 2024-01-09 |  |  | -162.5%
Sand ( Al kharj ) 1000 cum subject to consultant approval | 10 | 2024-01-10 | 2024-01-20 |  |  | -220%
Peatmoss from KSA supplier subject to consultant approval |  | 2024-01-21 | 2024-01-21
Pre seeding fertiliser 8:12:8 from KSA supplier for 1600 kg |  | 2024-01-22 | 2024-01-22
Project Technical Condition Survey |  | 2024-01-23 | 2024-01-23
Irrigation Booster pumps |  | 2024-01-24 | 2024-01-24
Inspection of the Pumps Mechanical Seal |  | 2024-01-25 | 2024-01-25
Inspection of the Mechanical Valves and PRSV |  | 2024-01-26 | 2024-01-26
Irrigation Tanks |  | 2024-01-27 | 2024-01-27
Inspection of the Mechanical gate valves and Float valve |  | 2024-01-28 | 2024-01-28
Irrigation Network |  | 2024-01-29 | 2024-01-29
Inspecting the Mainline HDPE pipes |  | 2024-01-30 | 2024-01-30
Inspecting the Air valves, Isolation valves and QCVs |  | 2024-01-31 | 2024-01-31
Inspecting the TORO Rotors performance |  | 2024-02-01 | 2024-02-01
Inspecting the air valves and QCVs |  | 2024-02-02 | 2024-02-02
Irrigation Smart Controller system |  | 2024-02-03 | 2024-02-03
Update Toro Lynx® Control System |  | 2024-02-04 | 2024-02-04
Renovation |  | 2024-02-05 | 2024-02-05
Turf Removal |  | 2024-02-06 | 2024-02-06
Cutting and removal of the existing turf surface using Wessex STC 180 Flail and Redexim Turf Stripper down to a maximum depth of 25mm below finished kerb level |  | 2024-02-07 | 2024-02-07
Aeration |  | 2024-02-08 | 2024-02-08
Aeration using Verti-drain set at maximum depth of 250mm |  | 2024-02-09 | 2024-02-09
Surface re-grading |  | 2024-02-10 | 2024-02-10
Consolidate the track surface using flat roller and irrigation |  | 2024-02-11 | 2024-02-11
Spread any required and approved sand and peat moss to correct any level discrepancies |  | 2024-02-12 | 2024-02-12
Drag mate finished surface to create seed bed |  | 2024-02-13 | 2024-02-13
Seeding |  | 2024-02-14 | 2024-02-14
Application of pre starter Fertilizer 8:12:8 applied as per approved MES |  | 2024-02-15 | 2024-02-15
Seeding -Poa pratensis ( applied as per approved MES ) 250 Kg/ha |  | 2024-02-16 | 2024-02-16
Seeding- Ryegrass ( applied as per approved MES ) 500 Kg/ha |  | 2024-02-17 | 2024-02-17
Turf Establishment |  | 2024-02-18 | 2024-02-18
Establish a turf surface, including any cultural practices (topdressing/rolling/aeration) |  | 2024-02-19 | 2024-02-19
Operate the irrigation system based on turf requirements |  | 2024-02-20 | 2024-02-20
Application of Fertilizer / Pesticide / Fungicide |  | 2024-02-21 | 2024-02-21
Incremental cutting heights in line with growth rates in order to achieve final desired turf cutting |  | 2024-02-22 | 2024-02-22
Establish the turf nursery |  | 2024-02-23 | 2024-02-23
Turf Maintenance |  | 2024-02-24 | 2024-02-24
Maintenace of turf surface, including any cultural practices |  | 2024-02-25 | 2024-02-25
Set irrigation parameters which allows for continuous root development, whilst maintaining |  | 2024-02-26 | 2024-02-26
Continue to apply turf apply fertilisers, fungicides and pesticides as per PPM schedule and |  | 2024-02-27 | 2024-02-27
Prepare turf track surface for race days, including positioning of temporary rails |  | 2024-02-28 | 2024-02-28
Post race turf track divot repairs |  | 2024-02-29 | 2024-02-29
|  | 2024-03-01 | 2024-03-01
Formulas:
Start = [Start, row above]+[Days]
Start = [End, row above]+1
End = IF([Days]=1,[Start]+[Days]-1,[Start]+[Days])